## Feuil1
NATIONAL INSTITUTE OF STATISTICS OF RWANDA SPECIFIC PROCUREMENT PLAN FOR THE YEAR 2012-2013
FROM JULY 2012 TO JUNE 2013
SPECIFIC PROCUREMENT PLAN /July 2012
N° | Title of tender | Type of contract | Estimated cost( in RWF) | Source of funds | Tendering method | Prequalification(Yes/No) | Preparation of T.Doc. |  |  |  | No objection on T.Doc. |  |  |  | Publication |  | Bid opening |  | Bid evaluation |  | Expertise required | No objection on evaluation report |  |  |  | Notification and contract signing |  | Recruitment of supervisor mission | Contract Management
[7 empty] | D |  | F |  | RPPA |  | Financing | [8 empty] | NTB | RPPA | Financing |  |  |  |  | D |  | F
| SPECIFIC PROCUREMENT PLAN / July, 2012 |  | 1566223721 |  |  |  | P | R | P | R | P | R | P | R | P | R | P | R | P | R |  | P | R | P | R | P | R |  | P | R | P | R
1 | Facilities for holding national and provincial dissemination of survey realized by NISR | Goods | 8000000 | UNICEF | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
2 | Insurance of vehicles used in the field by the National Institute of Statistics of Rwanda | Goods | 6000000 | NSDS B.F. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
3 | Insurance of field workers during the surveys organized by NISR. | Goods | 3000000 | NSDS B.F. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
4 | Publication of NISR Tenders, Articles, Announcements, etc. | Goods | 3000000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
5 | Publication of NISR tenders, articles, announcements, etc. | Goods | 3000000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
6 | Acquisition and maintenance of three (3) fax machines | Goods | 5000000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
7 | Supply of cafeteria consumables for NISR Staff | Goods | 22000000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
8 | Realization and production of publicity spots on radio and TV for sensitization. | Goods | 10000000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
9 | Sourcing sports service providers/NISR Staff for a period of two (2) years/framework contract for 2 years | Goods | 15000000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
10 | Event management and other related services for events organized by NISR | Goods | 7500000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
11 | Sourcing a specialized restaurant based in Kigali City for catering service at NISR | Goods | 10000000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
12 | Hosting and maintenance of NISR website | Goods | 1770000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
13 | Supply airtime and other related needs for NISR staff and fieldworkers | Goods | 15000000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
14 | Design, Printing and installation of banners, pull-ups and other related services | Goods | 5000000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
15 | Supply fuel and gasoline for all NISR vehicles on the field | Goods | 75000000 | NSDS B.F. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
16 | Supply office stationery, field workers materials and printing consumables | Goods | 33593121 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
17 | Supply of computer consumables including logistics materials to effectively deliver NISR activities | Goods | 2970000 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
18 | Cleaning service and protection flowers gardens at NISR building office | Goods | 11115600 | O.B. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
19 | Equipments and backup service's fees enhancing data access through diversif. of data dissem. | Goods | 10000000 | NSDS B.F. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
20 | National Agriculture Survey pilot conducted( supply of field workers materials and other facilities) | Goods | 1000000 | NSDS B.F. | NOCB | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
21 | Closer user group communication fees in order to develop mobile phones/RPHC | Goods | 17500000 | NSDS B.F. | RFQ | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
22 | Accomodation facilities for the third level training of enumerators, team supervisors and controllers | Goods | 1000000000 | SS or DC | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
23 | Supply of 17 modems and subscription coverage of 2 months for NISR staff | Goods | 1000000 | NSDS B.F. | RFQ | No | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
24 | Seeking for a qualified and experienced international survey data processing expert | Service | 54900000 | NSDS B.F. | IC | Yes | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
25 | Recruitment of an international individual consultant sampling expert | Service | 22875000 | NSDS B.F. | IC | Yes | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
26 | Provide technical advice and assistance/improving National Accounts and other key economic | Service | 150000000 | NSDS B.F. | QCBS | Yes | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
27 | Hiring an international consulting firm to help NISR to develop a strategy for developing a library | Service | 20000000 | NSDS B.F. | QCBS | Yes | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
28 | Recruitment of the consulting firm to develop and implement Mobile Phones SMS system | Service | 12000000 | NSDS B.F. | QCBS | Yes | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
29 | Seeking an international audit firm to conduct an independent audit of NISR financial statements | Service | 25000000 | NSDS B.F. | QCBS | Yes | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
30 | Recruitment of international individual consultant to review NSDS for year 2011/2012 | Service | 15000000 | NSDS B.F. | QCBS | Yes | 2012-07-02 | Not yet | 2012-07-04 | Not yet | No | No | No | No | 2012-07-10 | Not yet | 2012-08-14 | Not yet | 2012-08-21 | Not yet | No | No | No | No | No | 2012-09-07 | Not yet | No | 2012-09-11 | Not yet | 2012-09-15 | Not yet
SPECIFIC PROCUREMENT PLAN /August, 2012
N° | Title of tender | Type of contract | Estimated cost( in RWF) | Source of funds | Tendering method | Prequalification(Yes/No) | Preparation of T.Doc. |  |  |  | No objection on T.Doc. |  |  |  | Publication |  | Bid opening |  | Bid evaluation |  | Expertise required | No objection on evaluation report |  |  |  | Notification and contract signing |  | Recruitment of supervisor mission | Contract Management
[7 empty] | D |  | F |  | RPPA |  | Financing | [8 empty] | NTB | RPPA | Financing |  |  |  |  | D |  | F
| SPECIFIC PROCUREMENT PLAN / August, 2012 |  | 1577505000 |  |  |  | P | R | P | R | P | R | P | R | P | R | P | R | P | R |  | P | R | P | R | P | R |  | P | R | P | R
1 | Post -Enumeration Survey sensitisation and printing questionnaires, manuals and other related documents | Goods | 43200000 | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
2 | Post -Enumeration Survey sensitisation supply of field workers materials and equipments | Goods | 15000000 | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
3 | Supply of materials and equipments to be used in agriculture survey for season 2013(stationary, first aid kit and other) | Goods | 580000000 | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
4 | Internet hosting fees for the fiscal year 2012/2013 | Goods | 10800000 | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
5 | Supply of IT accessories including modems, software, switches, cabling, batteries and other items | Goods | 8500000 | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
6 | Hotels facilities for 500 coders and data entry staff trained and other facilities | Goods | 58405000 | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
7 | Contracting an insurance company to insure NISR building and assets completed | Goods | 20000000 | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
8 | Ensuring adequate provision of office supplies and consumables, stationeries, etc | Goods | 12000000 | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
9 | Maintenance of NISR building including spare parts needs fo years of maintenance | Goods | 15000000 | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
10 | Two(2) years contract for supply of office stationeries and field work materials and equip. | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
11 | Printing all NISR documents such as questionnaires, brochures, manuals, reports,etc | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
12 | Supply of insurance for 38 vehicles used in the field by NISR | Goods | 5100000 | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
13 | Hotels facilities and other accomodations for NISR trainings, workshops, conferences, etc. | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
14 | Facilities for holding national and provincial dissemination of cartography preliminary report | Service | 19500000 | NSDS B.F. | NOCB | Yes | 2012-08-02 | Not yet | 2012-08-04 | Not yet | No | No | No | No | 2012-08-08 | Not yet | 2012-09-12 | Not yet | 2012-09-19 | Not yet | No | No | No | No | No | 2012-10-06 | Not yet | No | 2012-10-11 | Not yet | 2012-10-15 | Not yet
15 | Recruitment of international firm to prepare interim EICV, analyse census data and other surveys conducted by NISR | Service | 250000000 | NSDS B.F. | IOCB | Yes | 2012-08-10 | Not yet | 2012-08-12 | Not yet | No | No | No | No | 2012-08-22 | Not yet | 2012-09-26 | Not yet | 2012-10-04 | Not yet | No | No | No | No | No | 2012-10-22 | Not yet | No | 2012-10-27 | Not yet | 2012-10-31 | Not yet
16 | Refurbishment of NISR building | Works | 540000000 | NSDS B.F. | NOCB | No | 2012-08-10 | Not yet | 2012-08-12 | Not yet | No | No | No | No | 2012-08-22 | Not yet | 2012-09-26 | Not yet | 2012-10-04 | Not yet | No | No | No | No | No | 2012-10-22 | Not yet | No | 2012-10-27 | Not yet | 2012-10-31 | Not yet
N° | Title of tender | Type of contract | Estimated cost( in RWF) | Source of funds | Tendering method | Prequalification(Yes/No) | Preparation of T.Doc. |  |  |  | No objection on T.Doc. |  |  |  | Publication |  | Bid opening |  | Bid evaluation |  | Expertise required | No objection on evaluation report |  |  |  | Notification and contract signing |  | Recruitment of supervisor mission | Contract Management
[7 empty] | D |  | F |  | RPPA |  | Financing | [8 empty] | NTB | RPPA | Financing |  |  |  |  | D |  | F
[7 empty] | P | R | P | R | P | R | P | R | P | R | P | R | P | R |  | P | R | P | R | P | R |  | P | R | P | R
| SPECIFIC PROCUREMENT PLAN / September, 2012 |  | 1007214160
1 | Transport for field materials provided(car, boats, manpower for loading and uploading | Goods | 809821760 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
2 | National Dissemination workshop facilities for EICV3 results/We will use SERENA HOTEL | Goods | 10000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
3 | Facilities for provincial dissemination workshops for EICV3 results | Goods | 21000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
4 | Organising national statistical day (incl. banners, posters, media coverage, facilities etc) | Goods | 9000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
5 | Hotels facilities for NISR trainings, workshops, conferences/LCD-DM project/September 2012 | Goods | 24692400 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
6 | Draft 2012 statistical year book produced(validation workshop facilitated, printing and others) | Goods | 1400000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
7 | Data sharing policy across NSS validated(technical and fcial inputs from Paris 21 and WB experts) | Goods | 1500000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
8 | Printing of business cards, badges, visitor's cards, stamps, etc, | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
9 | Supply of user group service for 150 persons for the upcoming 2012 RPHC Post-Enumeration Survey | Goods | 1000000 | NSDS B.F. | RFQ | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
10 | Supply of 3 external hard disks of 2TB and 40 SD memory cards for the staff of Agricultural Survey | Goods | 1000000 | NSDS B.F. | RFQ | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
11 | Supply of 60 magnifying glasses for the National Agricultural Survey | Goods | 1000000 | NSDS B.F. | RFQ | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
12 | Hotel facilities for NISR staff training, workshops for different surveys conducted by NISR | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
13 | Supply of ink cartridges, toners for printers and photocopiers used by NISR | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
14 | Supply of insurance of field workers during the surveys organized by NISR | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
15 | Publication of NISR tenders, articles, announcements, etc in reg. and intern.newspapers | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
16 | Acquisition and maintenance of three(3) fax machines | Goods | 4500000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
17 | Supply of cafeteria consumables for NISR staff | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
18 | Realization and production of publicity spots on radio and TV for sensitization | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
19 | Event management to cater for decoration services, cultural troupe, audio-video prod.etc… | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
20 | Sourcing a specialized restaurant based in Kigali City for catering service at NISR conf. | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
21 | Supply and installation of air conditioners as additional materials in the data entry | Goods | 10000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
22 | Recruitment of an international expert on GIS for 6 months | Service | 43000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
23 | Recruitment of National Procurement Expert for bulk procurement such as agriculture survey and other survey | Service | 14400000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
24 | Recruitment of intern.consultant for technical assistance for capacity development, data processing and archiving | Service | 54900000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-08 | Not yet | 2012-10-13 | Not yet | 2012-10-20 | Not yet | No | No | No | No | No | 2012-11-06 | Not yet | No | 2012-11-11 | Not yet | 2012-11-15 | Not yet
N° | Title of tender | Type of contract | Estimated cost( in RWF) | Source of funds | Tendering method | Prequalification(Yes/No) | Preparation of T.Doc. |  |  |  | No objection on T.Doc. |  |  |  | Publication |  | Bid opening |  | Bid evaluation |  | Expertise required | No objection on evaluation report |  |  |  | Notification and contract signing |  | Recruitment of supervisor mission | Contract Management
[7 empty] | D |  | F |  | RPPA |  | Financing | [8 empty] | NTB | RPPA | Financing |  |  |  |  | D |  | F
[7 empty] | P | R | P | R | P | R | P | R | P | R | P | R | P | R |  | P | R | P | R | P | R |  | P | R | P | R
| SPECIFIC PROCUREMENT PLAN / October, 2012 |  | 228277250
1 | Acquisition of 3500 archiving boxes and other archiving items for interim EICV | Goods | 12000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
2 | Publication of Preliminary census results (data and maps) | Goods | 6000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
3 | Repairing and maintenance of NISR vehicles | Goods | 30000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
4 | Hotels facilities for NISR trainings, workshops, conferences, etc for the month/October 2012 | Goods | 5000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
5 | Sensitisation and publicity on TV and Radio for Post-Enumeration Survey conducted(publicity spots, film, etc…...) | Goods | 3827250 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
6 | Training facilitation provided, data clerks, workshops on coverage analysis and other facilities | Goods | 15000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
7 | Scaels and materials purchased for CPI data collection | Goods | 1950000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
8 | National workshops and trainings facilitated | Goods | 15000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
9 | Training facilitation provided for field work/industrial statistics produced | Goods | 13500000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
10 | Supply and use table for 2011 base year produced/International TA firm contracted | Service | 78000000 | NSDS B.F. | NOCB | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
11 | Recruitment of consulting firm to develop and implement mobile phones/rapid SMS system | Service | 15000000 | NSDS B.F. | QCBS | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
12 | Recruitment of international company to develop a strategy for dev. A modern | Service | 10000000 | NSDS B.F. | QCBS | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
13 | Recruitment of international consultant to provide an independent yet view NSDS | Service | 13500000 | NSDS B.F. | IC | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
14 | Recruitment of internation consultant for sampling technical issues | Service | 9500000 | NSDS B.F. | IC | No | 2012-09-02 | Not yet | 2012-09-04 | Not yet | No | No | No | No | 2012-09-20 | Not yet | 2012-10-25 | Not yet | 2012-11-01 | Not yet | No | No | No | No | No | 2012-11-19 | Not yet | No | 2012-11-26 | Not yet | 2012-11-30 | Not yet
| Title of tender | Type of contract | Estimated cost( in RWF) | Source of funds | Tendering method | Prequalification(Yes/No) | Preparation of T.Doc. |  |  |  | No objection on T.Doc. |  |  |  | Publication |  | Bid opening |  | Bid evaluation |  | Expertise required | No objection on evaluation report |  |  |  | Notification and contract signing |  | Recruitment of supervisor mission | Contract Management
[7 empty] | D |  | F |  | RPPA |  | Financing | [8 empty] | NTB | RPPA | Financing |  |  |  |  | D |  | F
[7 empty] | P | R | P | R | P | R | P | R | P | R | P | R | P | R |  | P | R | P | R | P | R |  | P | R | P | R
| SPECIFIC PROCUREMENT PLAN / November, 2012 |  | 61550000
1 | Recruitment of Consultant to update questionnaires stored in accordance with standard archiving norms and All survey materials stored electronically (CD) and backed up adequately | Goods | 7500000 | UNFPA | NOCB | No | 2012-10-02 | Not yet | 2012-10-04 | Not yet | No | No | No | No | 2012-10-08 | Not yet | 2012-11-12 | Not yet | 2012-11-19 | Not yet | No | No | No | No | No | 2012-12-06 | Not yet | No | 2012-12-11 | Not yet | 2012-12-15 | Not yet
2 | Sourcing of company to be printed the preliminary results of the census published | Goods | 5950000 | NSDS B.F. | NOCB | No | 2012-10-02 | Not yet | 2012-10-04 | Not yet | No | No | No | No | 2012-10-08 | Not yet | 2012-11-12 | Not yet | 2012-11-19 | Not yet | No | No | No | No | No | 2012-12-06 | Not yet | No | 2012-12-11 | Not yet | 2012-12-15 | Not yet
3 | Hotels facilities for NISR trainings, workshops, conferences, etc for the month/November 2012 | Goods | 5000000 | NSDS B.F. | NOCB | No | 2012-10-02 | Not yet | 2012-10-04 | Not yet | No | No | No | No | 2012-10-08 | Not yet | 2012-11-12 | Not yet | 2012-11-19 | Not yet | No | No | No | No | No | 2012-12-06 | Not yet | No | 2012-12-11 | Not yet | 2012-12-15 | Not yet
4 | Dissemination workshop of new GDP benchmark arranged | Goods | 3900000 | NSDS B.F. | NOCB | No | 2012-10-02 | Not yet | 2012-10-04 | Not yet | No | No | No | No | 2012-10-08 | Not yet | 2012-11-12 | Not yet | 2012-11-19 | Not yet | No | No | No | No | No | 2012-12-06 | Not yet | No | 2012-12-11 | Not yet | 2012-12-15 | Not yet
5 | Printing of books, leaflets and other documents for EICV3 results dissemination | Goods | 23200000 | NSDS B.F. | NOCB | No | 2012-10-02 | Not yet | 2012-10-04 | Not yet | No | No | No | No | 2012-10-08 | Not yet | 2012-11-12 | Not yet | 2012-11-19 | Not yet | No | No | No | No | No | 2012-12-06 | Not yet | No | 2012-12-11 | Not yet | 2012-12-15 | Not yet
6 | Dissemination of preliminary results of 2012 Rwanda Population and Housing Census( reports,etc…) | Goods | 4000000 | NSDS B.F. | NOCB | No | 2012-10-02 | Not yet | 2012-10-04 | Not yet | No | No | No | No | 2012-10-08 | Not yet | 2012-11-12 | Not yet | 2012-11-19 | Not yet | No | No | No | No | No | 2012-12-06 | Not yet | No | 2012-12-11 | Not yet | 2012-12-15 | Not yet
7 | Enhancing NISR corporate image(design and editorial support, new firm recruited, etc…….) | Goods | 5000000 | NSDS B.F. | NOCB | No | 2012-10-02 | Not yet | 2012-10-04 | Not yet | No | No | No | No | 2012-10-08 | Not yet | 2012-11-12 | Not yet | 2012-11-19 | Not yet | No | No | No | No | No | 2012-12-06 | Not yet | No | 2012-12-11 | Not yet | 2012-12-15 | Not yet
8 | Organization of annual celebration of statistical day/hig level authorities invited and hotel facilities | Goods | 7000000 | NSDS B.F. | NOCB | No | 2012-10-02 | Not yet | 2012-10-04 | Not yet | No | No | No | No | 2012-10-08 | Not yet | 2012-11-12 | Not yet | 2012-11-19 | Not yet | No | No | No | No | No | 2012-12-06 | Not yet | No | 2012-12-11 | Not yet | 2012-12-15 | Not yet
| Title of tender | Type of contract | Estimated cost( in RWF) | Source of funds | Tendering method | Prequalification(Yes/No) | Preparation of T.Doc. |  |  |  | No objection on T.Doc. |  |  |  | Publication |  | Bid opening |  | Bid evaluation |  | Expertise required | No objection on evaluation report |  |  |  | Notification and contract signing |  | Recruitment of supervisor mission | Contract Management
[7 empty] | D |  | F |  | RPPA |  | Financing | [8 empty] | NTB | RPPA | Financing |  |  |  |  | D |  | F
[7 empty] | P | R | P | R | P | R | P | R | P | R | P | R | P | R |  | P | R | P | R | P | R |  | P | R | P | R
| SPECIFIC PROCUREMENT PLAN / December, 2012 |  | 297316800
1 | Supply of tires for all NISR Vehicles | Goods | 65500000 | NSDS B.F. | NOCB | No | 2012-11-05 | Not yet | 2012-11-07 | Not yet | No | No | No | No | 2012-11-21 | Not yet | 2012-12-26 | Not yet | 2013-01-02 | Not yet | No | No | No | No | No | 2013-01-20 | Not yet | No | 2013-01-26 | Not yet | 2013-01-30 | Not yet
2 | Hotels facilities for NISR trainings, workshops, conferences, etc for the month/December 2012 | Goods | 5000000 | NSDS B.F. | NOCB | No | 2012-11-05 | Not yet | 2012-11-07 | Not yet | No | No | No | No | 2012-11-21 | Not yet | 2012-12-26 | Not yet | 2013-01-02 | Not yet | No | No | No | No | No | 2013-01-20 | Not yet | No | 2013-01-26 | Not yet | 2013-01-30 | Not yet
3 | Facilities for holding of the national and provincial dissemination of preliminary Census results | Goods | 8950000 | NSDS B.F. | NOCB | No | 2012-11-05 | Not yet | 2012-11-07 | Not yet | No | No | No | No | 2012-11-21 | Not yet | 2012-12-26 | Not yet | 2013-01-02 | Not yet | No | No | No | No | No | 2013-01-20 | Not yet | No | 2013-01-26 | Not yet | 2013-01-30 | Not yet
4 | Publication of one page contents in international newspaper like The Economist, CommonWealthYearBook,etc……. | Goods | 14500000 | NSDS B.F. | NOCB | No | 2012-11-05 | Not yet | 2012-11-07 | Not yet | No | No | No | No | 2012-11-21 | Not yet | 2012-12-26 | Not yet | 2013-01-02 | Not yet | No | No | No | No | No | 2013-01-20 | Not yet | No | 2013-01-26 | Not yet | 2013-01-30 | Not yet
5 | Hiring of a recording room for producing a CD for census matter trainers at all levels of training | Goods | 1000000 | NSDS B.F. | RFQ | No | 2012-11-05 | Not yet | 2012-11-07 | Not yet | No | No | No | No | 2012-11-21 | Not yet | 2012-12-26 | Not yet | 2013-01-02 | Not yet | No | No | No | No | No | 2013-01-20 | Not yet | No | 2013-01-26 | Not yet | 2013-01-30 | Not yet
6 | Recruitment of international Consultant for CPI (US Bureau of Labor Statistics) | Service | 10200000 | NSDS B.F. | NOCB | No | 2012-11-05 | Not yet | 2012-11-07 | Not yet | No | No | No | No | 2012-11-21 | Not yet | 2012-12-26 | Not yet | 2013-01-02 | Not yet | No | No | No | No | No | 2013-01-20 | Not yet | No | 2013-01-26 | Not yet | 2013-01-30 | Not yet
7 | Second phase-Consulting firm for improving Rwanda Agriculture Statistics System | Service | 192166800 | NSDS B.F. | IOCB | No | 2012-11-05 | Not yet | 2012-11-07 | Not yet | No | No | No | No | 2012-11-21 | Not yet | 2012-12-26 | Not yet | 2013-01-02 | Not yet | No | No | No | No | No | 2013-01-20 | Not yet | No | 2013-01-26 | Not yet | 2013-01-30 | Not yet
8 | Maintenance of all NISR vehicles for a period of two (2) years | Service | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2012-11-05 | Not yet | 2012-11-07 | Not yet | No | No | No | No | 2012-11-21 | Not yet | 2012-12-26 | Not yet | 2013-01-02 | Not yet | No | No | No | No | No | 2013-01-20 | Not yet | No | 2013-01-26 | Not yet | 2013-01-30 | Not yet
| Title of tender | Type of contract | Estimated cost( in RWF) | Source of funds | Tendering method | Prequalification(Yes/No) | Preparation of T.Doc. |  |  |  | No objection on T.Doc. |  |  |  | Publication |  | Bid opening |  | Bid evaluation |  | Expertise required | No objection on evaluation report |  |  |  | Notification and contract signing |  | Recruitment of supervisor mission | Contract Management
[7 empty] | D |  | F |  | RPPA |  | Financing | [8 empty] | NTB | RPPA | Financing |  |  |  |  | D |  | F
[7 empty] | P | R | P | R | P | R | P | R | P | R | P | R | P | R |  | P | R | P | R | P | R |  | P | R | P | R
| SPECIFIC PROCUREMENT PLAN / January, 2013 |  | 221605040
1 | Printing and binding of statistical year book | Goods | 9000000 | NSDS B.F. | NOCB | No | 2012-12-05 | Not yet | 2012-12-07 | Not yet | No | No | No | No | 2012-12-21 | Not yet | 2013-01-25 | Not yet | 2013-02-01 | Not yet | No | No | No | No | No | 2013-02-19 | Not yet | No | 2013-02-24 | Not yet | 2013-02-28 | Not yet
2 | Replacing old IT infrastructure (PCs, laptops, servers etc) | Goods | 150000000 | NSDS B.F. | NOCB | No | 2012-12-05 | Not yet | 2012-12-07 | Not yet | No | No | No | No | 2012-12-21 | Not yet | 2013-01-25 | Not yet | 2013-02-01 | Not yet | No | No | No | No | No | 2013-02-19 | Not yet | No | 2013-02-24 | Not yet | 2013-02-28 | Not yet
3 | Procurement process for the supply of field equipments completed by June 2013 | Goods | 3000000 | NSDS B.F. | NOCB | No | 2012-12-05 | Not yet | 2012-12-07 | Not yet | No | No | No | No | 2012-12-21 | Not yet | 2013-01-25 | Not yet | 2013-02-01 | Not yet | No | No | No | No | No | 2013-02-19 | Not yet | No | 2013-02-24 | Not yet | 2013-02-28 | Not yet
4 | Training facilities of interim EICV enumerators(hotel facilities and other services) | Goods | 5000000 | NSDS B.F. | NOCB | No | 2012-12-05 | Not yet | 2012-12-07 | Not yet | No | No | No | No | 2012-12-21 | Not yet | 2013-01-25 | Not yet | 2013-02-01 | Not yet | No | No | No | No | No | 2013-02-19 | Not yet | No | 2013-02-24 | Not yet | 2013-02-28 | Not yet
5 | Printing and binding of questionnaires and other documents for interim EICV | Goods | 7500000 | NSDS B.F. | NOCB | No | 2012-12-05 | Not yet | 2012-12-07 | Not yet | No | No | No | No | 2012-12-21 | Not yet | 2013-01-25 | Not yet | 2013-02-01 | Not yet | No | No | No | No | No | 2013-02-19 | Not yet | No | 2013-02-24 | Not yet | 2013-02-28 | Not yet
6 | Accomodation service and other facilities for the year 2013/2014 | Goods | 30000000 | NSDS B.F. | NOCB | No | 2012-12-05 | Not yet | 2012-12-07 | Not yet | No | No | No | No | 2012-12-21 | Not yet | 2013-01-25 | Not yet | 2013-02-01 | Not yet | No | No | No | No | No | 2013-02-19 | Not yet | No | 2013-02-24 | Not yet | 2013-02-28 | Not yet
7 | Ceremony of awarding certificates to the institutions who have supported NISR during 08-12/RHPC | Goods | 1200000 | NSDS B.F. | RFQ | No | 2012-12-05 | Not yet | 2012-12-07 | Not yet | No | No | No | No | 2012-12-21 | Not yet | 2013-01-25 | Not yet | 2013-02-01 | Not yet | No | No | No | No | No | 2013-02-19 | Not yet | No | 2013-02-24 | Not yet | 2013-02-28 | Not yet
8 | Supply of IT accessories including modems, software, switches, cabling for data entry rooms and others | Goods | 650000 | NSDS B.F. | RFQ | No | 2012-12-05 | Not yet | 2012-12-07 | Not yet | No | No | No | No | 2012-12-21 | Not yet | 2013-01-25 | Not yet | 2013-02-01 | Not yet | No | No | No | No | No | 2013-02-19 | Not yet | No | 2013-02-24 | Not yet | 2013-02-28 | Not yet
9 | Recruitment of NISR ICT Equipments for two (2) years | Goods | 15255040 | NSDS B.F. | NOCB | No | 2012-12-05 | Not yet | 2012-12-07 | Not yet | No | No | No | No | 2012-12-21 | Not yet | 2013-01-25 | Not yet | 2013-02-01 | Not yet | No | No | No | No | No | 2013-02-19 | Not yet | No | 2013-02-24 | Not yet | 2013-02-28 | Not yet
| SPECIFIC PROCUREMENT PLAN/ February, 2013 |  | 70200000
1 | Cleaning service and protection flowers gardens at NISR building office | Goods | 12000000 | NSDS Basket Fund | NOCB | No | 2013-01-05 | Not yet | 2013-01-07 | Not yet | No | No | No | No | 2013-01-21 | Not yet | 2013-02-25 | Not yet | 2013-03-04 | Not yet | No | No | No | No | No | 2013-03-22 | Not yet | No | 2013-03-27 | Not yet | 2013-03-31 | Not yet
2 | Supply and installation of symantec antivirus to protect all NISR computers/300 users | Goods | 2500000 | NSDS Basket Fund | NOCB | No | 2013-01-05 | Not yet | 2013-01-07 | Not yet | No | No | No | No | 2013-01-21 | Not yet | 2013-02-25 | Not yet | 2013-03-04 | Not yet | No | No | No | No | No | 2013-03-22 | Not yet | No | 2013-03-27 | Not yet | 2013-03-31 | Not yet
3 | Supply of insurance of 20 NISR vehicles | Goods | 2500000 | NSDS B.F. | NOCB | No | 2013-01-05 | Not yet | 2013-01-07 | Not yet | No | No | No | No | 2013-01-21 | Not yet | 2013-02-25 | Not yet | 2013-03-04 | Not yet | No | No | No | No | No | 2013-03-22 | Not yet | No | 2013-03-27 | Not yet | 2013-03-31 | Not yet
4 | Recruitment of international Consultant for PPI (US Bureau of Labor Statistics) | Service | 10200000 | NSDS Basket Fund | SS or DC | No | 2013-01-05 | Not yet | 2013-01-07 | Not yet | No | No | No | No | 2013-01-21 | Not yet | 2013-02-25 | Not yet | 2013-03-04 | Not yet | No | No | No | No | No | 2013-03-22 | Not yet | No | 2013-03-27 | Not yet | 2013-03-31 | Not yet
5 | Recruit.of National two (2) Proc.Experts to review all proc. filing system in order to prepare audit 2011/2012 | Service | 3000000 | NSDS Basket Fund | IC | No | 2013-01-05 | Not yet | 2013-01-07 | Not yet | No | No | No | No | 2013-01-21 | Not yet | 2013-02-25 | Not yet | 2013-03-04 | Not yet | No | No | No | No | No | 2013-03-22 | Not yet | No | 2013-03-27 | Not yet | 2013-03-31 | Not yet
6 | Recruitment of international firm to provide technical assistance in the field of agricultural | Service | 40000000 | NSDS Basket Fund | QCBS | No | 2013-01-05 | Not yet | 2013-01-07 | Not yet | No | No | No | No | 2013-01-21 | Not yet | 2013-02-25 | Not yet | 2013-03-04 | Not yet | No | No | No | No | No | 2013-03-22 | Not yet | No | 2013-03-27 | Not yet | 2013-03-31 | Not yet
| SPECIFIC PROCUREMENT PLAN/ March, 2013 |  | 146530000
1 | Workshop facilities with stakeholders for Improving livestock and poultry statistics forecasting | Goods | 8500000 | O.B. | NOCB | No | 2013-02-05 | Not yet | 2013-02-07 | Not yet | No | No | No | No | 2013-02-21 | Not yet | 2013-03-28 | Not yet | 2013-04-04 | Not yet | No | No | No | No | No | 2013-04-22 | Not yet | No | 2013-04-26 | Not yet | 2013-04-30 | Not yet
2 | Workshop facilities to disseminate livestock and poultry statistics forecasting and other agricultural statistics | Goods | 4500000 | O.B. | NOCB | No | 2013-02-05 | Not yet | 2013-02-07 | Not yet | No | No | No | No | 2013-02-21 | Not yet | 2013-03-28 | Not yet | 2013-04-04 | Not yet | No | No | No | No | No | 2013-04-22 | Not yet | No | 2013-04-26 | Not yet | 2013-04-30 | Not yet
3 | Supply of cleaning materials and other materials for maintenance of NISR toilets | Goods | 980000 | O.B. | RFQ | No | 2013-02-05 | Not yet | 2013-02-07 | Not yet | No | No | No | No | 2013-02-21 | Not yet | 2013-03-28 | Not yet | 2013-04-04 | Not yet | No | No | No | No | No | 2013-04-22 | Not yet | No | 2013-04-26 | Not yet | 2013-04-30 | Not yet
4 | Supply of DG fridge, carpets and other materials for office facilitities | Goods | 750000 | O.B. | RFQ | No | 2013-02-05 | Not yet | 2013-02-07 | Not yet | No | No | No | No | 2013-02-21 | Not yet | 2013-03-28 | Not yet | 2013-04-04 | Not yet | No | No | No | No | No | 2013-04-22 | Not yet | No | 2013-04-26 | Not yet | 2013-04-30 | Not yet
5 | Supply of 60 scale rulers for agricultural survey | Goods | 400000 | O.B. | RFQ | No | 2013-02-05 | Not yet | 2013-02-07 | Not yet | No | No | No | No | 2013-02-21 | Not yet | 2013-03-28 | Not yet | 2013-04-04 | Not yet | No | No | No | No | No | 2013-04-22 | Not yet | No | 2013-04-26 | Not yet | 2013-04-30 | Not yet
6 | Supply of changeover switch for the generator plus installation | Goods | 900000 | O.B. | RFQ | No | 2013-02-05 | Not yet | 2013-02-07 | Not yet | No | No | No | No | 2013-02-21 | Not yet | 2013-03-28 | Not yet | 2013-04-04 | Not yet | No | No | No | No | No | 2013-04-22 | Not yet | No | 2013-04-26 | Not yet | 2013-04-30 | Not yet
7 | Reactivation of short code rapid sms/RURA service provider/Upcoming RPHC | Goods | 500000 | O.B. | RFQ | No | 2013-02-05 | Not yet | 2013-02-07 | Not yet | No | No | No | No | 2013-02-21 | Not yet | 2013-03-28 | Not yet | 2013-04-04 | Not yet | No | No | No | No | No | 2013-04-22 | Not yet | No | 2013-04-26 | Not yet | 2013-04-30 | Not yet
8 | Providing hotel services in Kigali City-Medium Level with at least a capacity to host 200 participants | Goods | Fram. contract/2years | O.B. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
9 | Sourcing of hotels to organize conference facilities and accomodation sces and other logist.requir.outside Kigali | Goods | Fram .contract/2years | O.B. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
10 | Providing VIP hotel services for all VIP events such as dissemination of results at national level and others | Goods | Fram. contract/2years | O.B. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
11 | Recruitment of local individual consultants(10 pers) for data analysis to support RPHC | Service | 40000000 | NSDS B.F. | IC | No | 2013-02-05 | Not yet | 2013-02-07 | Not yet | No | No | No | No | 2013-02-21 | Not yet | 2013-03-28 | Not yet | 2013-04-04 | Not yet | No | No | No | No | No | 2013-04-22 | Not yet | No | 2013-04-26 | Not yet | 2013-04-30 | Not yet
12 | Recruitment of loca individual consultant as national coordinator of EICV4 | Service | 65000000 | NSDS B.F. | IC | No | 2013-02-05 | Not yet | 2013-02-07 | Not yet | No | No | No | No | 2013-02-21 | Not yet | 2013-03-28 | Not yet | 2013-04-04 | Not yet | No | No | No | No | No | 2013-04-22 | Not yet | No | 2013-04-26 | Not yet | 2013-04-30 | Not yet
13 | Recruitment of NISR technical advisor to DG for curtain period | Service | 25000000 | NSDS B.F. | IC | No | 2013-02-05 | Not yet | 2013-02-07 | Not yet | No | No | No | No | 2013-02-21 | Not yet | 2013-03-28 | Not yet | 2013-04-04 | Not yet | No | No | No | No | No | 2013-04-22 | Not yet | No | 2013-04-26 | Not yet | 2013-04-30 | Not yet
| Title of tender | Type of contract | Estimated cost( in RWF) | Source of funds | Tendering method | Prequalification(Yes/No) | Preparation of T.Doc. |  |  |  | No objection on T.Doc. |  |  |  | Publication |  | Bid opening |  | Bid evaluation |  | Expertise required | No objection on evaluation report |  |  |  | Notification and contract signing |  | Recruitment of supervisor mission | Contract Management
[7 empty] | D |  | F |  | RPPA |  | Financing | [8 empty] | NTB | RPPA | Financing |  |  |  |  | D |  | F
[7 empty] | P | R | P | R | P | R | P | R | P | R | P | R | P | R |  | P | R | P | R | P | R |  | P | R | P | R
| SPECIFIC PROCUREMENT PLAN/ April, 2013 |  | 289323841
1 | Publication of the statistical tabulations on final Census results | Goods | 6000000 | O.B. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
2 | Supply of fuel and gasoline for all NISR vehicles used in the field during the data collection | Goods | 60000000 | O.B. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
3 | Designing and printing final results of the Census (folders, charts, posters, pullups, etc) | Goods | 6000000 | O.B. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
4 | Facilities for training and validation workshops for Rebasing GDP estimates and other hotel facilities | Goods | 1500000 | NSDS B.F. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
5 | Facilities for Census Thematic Analyses workshops | Goods | 6750000 | O.B. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
6 | Supply of 16 modems to be used by top management staff and wireless internet subscription | Goods | 3000000 | O.B. | RFQ | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
7 | Hiring space storage and archiving of 2012 RPHC materials/Renewable contract for one year period | Goods | 115275313 | O.B. | SS or DC | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
8 | Supply of 50 medical tool kits to be used on agricultural survey | Goods | 1000000 | O.B. | RFQ | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
9 | Supply of 60 batteries to be used in electronic scales used by price data collectors | Goods | 200000 | O.B. | RFQ | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
10 | Broadcast on radio Rwanda as well as community radios and on Rwaanda television | Goods | 2500000 | Framework contract |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
11 | Cleaning service and protection flowers gardens at NISR building /new contract | Goods | 27198528 | O.B. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
12 | Supply of 217 tires for NISR vehicles | Goods | 40000000 | NSDS B.F. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
13 | Design, printing and installation of billboards, banners of any size, pull up banners and other materials | Goods | Framework contract/2years | NSDS B.F. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
14 | Printing of business cards, ID cards, invitation cards, greeting cards, badges for NISR staff | Goods | Framework contract/2years | NSDS B.F. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
15 | Supply of airtime for NISR staff and field workers | Goods | Framework contract/2years | NSDS B.F. | NOCB | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
16 | Supply of 416 modems including airtimes for NISR field workers | Goods | 6500000 | O.B. | RFQ | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
17 | Sub-contract IFORD to undertake Census Data Analysis | Service | 13400000 | UNFPA | QCBS | No | 2013-03-05 | Not yet | 2013-03-07 | Not yet | No | No | No | No | 2013-03-19 | Not yet | 2013-04-23 | Not yet | 2013-04-30 | Not yet | No | No | No | No | No | 2013-05-20 | Not yet | No | 2013-05-26 | Not yet | 2013-05-30 | Not yet
| SPECIFIC PROCUREMENT PLAN/ May, 2013 |  | 112050000
1 | Security service at the National Institute of Statistics of Rwanda | Goods | 18000000 | NSDS B.F. | NOCB | No | 2013-04-01 | Not yet | 2013-04-03 | Not yet | No | No | No | No | 2013-04-07 | Not yet | 2013-05-12 | Not yet | 2013-05-19 | Not yet | No | No | No | No | No | 2013-06-06 | Not yet | No | 2013-06-11 | Not yet | 2013-06-15 | Not yet
2 | Hotel facilities for meetings, workshops, seminars and general meetings with NISR Staff | Goods | F.Contract for 2 years | NSDS B.F. | NOCB | No | 2013-04-01 | Not yet | 2013-04-03 | Not yet | No | No | No | No | 2013-04-07 | Not yet | 2013-05-12 | Not yet | 2013-05-19 | Not yet | No | No | No | No | No | 2013-06-06 | Not yet | No | 2013-06-11 | Not yet | 2013-06-15 | Not yet
3 | Supply of 3 tents for hire to protect NISR assets to disposed | Goods | 1000000 | NSDS B.F. | RFQ | No | 2013-04-01 | Not yet | 2013-04-03 | Not yet | No | No | No | No | 2013-04-07 | Not yet | 2013-05-12 | Not yet | 2013-05-19 | Not yet | No | No | No | No | No | 2013-06-06 | Not yet | No | 2013-06-11 | Not yet | 2013-06-15 | Not yet
4 | Short message peer to peer activation for IT system | Goods | 500000 | NSDS B.F. | RFQ | No | 2013-04-01 | Not yet | 2013-04-03 | Not yet | No | No | No | No | 2013-04-07 | Not yet | 2013-05-12 | Not yet | 2013-05-19 | Not yet | No | No | No | No | No | 2013-06-06 | Not yet | No | 2013-06-11 | Not yet | 2013-06-15 | Not yet
5 | Supply of 60 Global Positioning Systems(GPS) to the National Institute of Statistics of Rwanda | Goods | 37500000 | NSDS B.F. | NOCB | No | 2013-04-01 | Not yet | 2013-04-03 | Not yet | No | No | No | No | 2013-04-07 | Not yet | 2013-05-12 | Not yet | 2013-05-19 | Not yet | No | No | No | No | No | 2013-06-06 | Not yet | No | 2013-06-11 | Not yet | 2013-06-15 | Not yet
6 | Enhancing data access through diversification of data dissemination tools and updating existing tools | Goods | 17850000 | NSDS B.F. | NOCB | No | 2013-04-01 | Not yet | 2013-04-03 | Not yet | No | No | No | No | 2013-04-07 | Not yet | 2013-05-12 | Not yet | 2013-05-19 | Not yet | No | No | No | No | No | 2013-06-06 | Not yet | No | 2013-06-11 | Not yet | 2013-06-15 | Not yet
7 | Suppy of IT equipments including modems, softwares, swichts, cabling, batteries of UPS and other IT equip. | Goods | 3500000 | NSDS B.F. | NOCB | No | 2013-04-01 | Not yet | 2013-04-03 | Not yet | No | No | No | No | 2013-04-07 | Not yet | 2013-05-12 | Not yet | 2013-05-19 | Not yet | No | No | No | No | No | 2013-06-06 | Not yet | No | 2013-06-11 | Not yet | 2013-06-15 | Not yet
8 | Supply of 14 modems with internet service supply for 6 months for RPHC data analysits | Goods | 700000 | NSDS B.F. | RFQ | No | 2013-04-01 | Not yet | 2013-04-03 | Not yet | No | No | No | No | 2013-04-07 | Not yet | 2013-05-12 | Not yet | 2013-05-19 | Not yet | No | No | No | No | No | 2013-06-06 | Not yet | No | 2013-06-11 | Not yet | 2013-06-15 | Not yet
9 | Maintenaning and updating IT licenses | Service | 18000000 | NSDS B.F. | NOCB | No | 2013-04-01 | Not yet | 2013-04-03 | Not yet | No | No | No | No | 2013-04-07 | Not yet | 2013-05-12 | Not yet | 2013-05-19 | Not yet | No | No | No | No | No | 2013-06-06 | Not yet | No | 2013-06-11 | Not yet | 2013-06-15 | Not yet
10 | Recruitment of individual consultant as part of the NSDS Coordination Team | Service | 15000000 | NSDS B.F. | QCBS | No | 2013-04-01 | Not yet | 2013-04-03 | Not yet | No | No | No | No | 2013-04-07 | Not yet | 2013-05-12 | Not yet | 2013-05-19 | Not yet | No | No | No | No | No | 2013-06-06 | Not yet | No | 2013-06-11 | Not yet | 2013-06-15 | Not yet
N° | Title of tender | Type of contract | Estimated cost( in RWF) | Source of funds | Tendering method | Prequalification(Yes/No) | Preparation of T.Doc. |  |  |  | No objection on T.Doc. |  |  |  | Publication |  | Bid opening |  | Bid evaluation |  | Expertise required | No objection on evaluation report |  |  |  | Notification and contract signing |  | Recruitment of supervisor mission | Contract Management
[7 empty] | D |  | F |  | RPPA |  | Financing | [8 empty] | NTB | RPPA | Financing |  |  |  |  | D |  | F
[7 empty] | P | R | P | R | P | R | P | R | P | R | P | R | P | R |  | P | R | P | R | P | R |  | P | R | P | R
| SPECIFIC PROCUREMENT PLAN/ June, 2013 |  | 55300000
1 | Facilities for Census 2nd and 3rd Thematic Analyses workshops | Goods | 24800000 | O.B. | NOCB | No | 2013-05-02 | Not yet | 2013-05-04 | Not yet | No | No | No | No | 2013-04-18 | Not yet | 2013-05-23 | Not yet | 2013-05-30 | Not yet | No | No | No | No | No | 2013-06-19 | Not yet | No | 2013-06-26 | Not yet | 2013-06-30 | Not yet
2 | Facilities for 1-day dissemination workshop for Rebasing GDP estimates | Goods | 5000000 | NSDS B.F. | NOCB | No | 2013-05-02 | Not yet | 2013-05-04 | Not yet | No | No | No | No | 2013-04-18 | Not yet | 2013-05-23 | Not yet | 2013-05-30 | Not yet | No | No | No | No | No | 2013-06-19 | Not yet | No | 2013-06-26 | Not yet | 2013-06-30 | Not yet
3 | Insurance for all NISR vehicles used in the field by NISR | Goods | 4500000 | NSDS B.F. | NOCB | No | 2013-05-02 | Not yet | 2013-05-04 | Not yet | No | No | No | No | 2013-04-18 | Not yet | 2013-05-23 | Not yet | 2013-05-30 | Not yet | No | No | No | No | No | 2013-06-19 | Not yet | No | 2013-06-26 | Not yet | 2013-06-30 | Not yet
4 | Supply and installation of a water pump to permit water to reach upper floors, | Goods | 1000000 | NSDS B.F. | NOCB | No | 2013-05-02 | Not yet | 2013-05-04 | Not yet | No | No | No | No | 2013-04-18 | Not yet | 2013-05-23 | Not yet | 2013-05-30 | Not yet | No | No | No | No | No | 2013-06-19 | Not yet | No | 2013-06-26 | Not yet | 2013-06-30 | Not yet
5 | Hotel facilities for meetings, workshops, seminars and general meetings with NISR Staff | Goods | F.C. for 2 years | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
6 | Supply and installation of curtains for NISR building | Goods | 20000000 | NSDS B.F. | NOCB | No | 2013-05-02 | Not yet | 2013-05-04 | Not yet | No | No | No | No | 2013-04-18 | Not yet | 2013-05-23 | Not yet | 2013-05-30 | Not yet | No | No | No | No | No | 2013-06-19 | Not yet | No | 2013-06-26 | Not yet | 2013-06-30 | Not yet
| TOTAL AMOUNT / From 31st July, 2012 to 30th June, 2013 |  | 5633095812
B.F: BASKET FUND
NSDS Basket Fund: National Statistical Development Strategies Basket Fund
RF: Request for Quotations/Shopping
EOI: Expression Of Interest for services
NOCBM: National Open Competitive Bidding Method
IOCBM: International Open Competitive Bidding Method
RTM : Restricted Tendering Method
QCBS : Quality & Cost Based Selection
SS Or DC: Single Source: Entente Directe ou Marché de Gré à Gré ( Direct Contracting)
OB :Ordinary Budget
R-DHS: Rwanda Demographic Health Survey
NISR : National Institute of Statistics of Rwanda
ICT: Information & Communication Technology
UNFPA: United Nations Population Fund
ICP: International Comparison Program
UNICEF: United Nations Children's Fund
LCD-DM: Local Capacity Development in Data Management Project
UNDP: United Nations Development Program
ADB: African Development Bank
MSP: Manpower Survey Project
2012 RPHC: 2012 Rwanda Population and Housing Census
RPPA: Rwanda Public Procurement Authority
TD: Tender Document
IC: Individual Consultant
CQS: Selection Based on the Consultant’s Qualifications
| Prepared on 30th July 2012 by: | [21 empty] | Approuved by:
| Eric BUGINGO | [21 empty] | Odette MBABAZI
| Procurement Officer/National Institute of Statistics of Rwanda | [21 empty] | Deputy Director General of Corporate Services
Alphonse SHUMBUSHO
Procurement Officer/National Institute of Statistics of Rwanda
Formulas:
F = SUM([Preparation of T.Doc.]+2)
F = SUM([Contract Management]+4)
Bid opening = SUM([Publication]+35)
Bid evaluation = SUM([Bid opening]+7)
Notification and contract signing = SUM([Bid evaluation]+17)
Contract Management = SUM([Notification and contract signing]+4)